## Schedules
Schedule - List - **Addition w/Bath - Raised Foundation** (exported on Feb 18, 2022)
ID # | Title | Marked Complete | Phase | Dur. | Start | End | Assigned To | Confirm Accepted Count | Confirm Pending Count | Confirm Declined Count | Pred | Pred 1 Lag
1 | Excavation/ footings | TRUE |  | 5 | 2016-12-01 | 2016-12-07 | General Contracting | 0 | 0 | 1
2 | Footing Inspection | TRUE |  | 1 | 2016-12-08 | 2016-12-08 | N/A | 0 | 0 | 0 | 1 FS | 0
3 | Pour footings | TRUE |  | 1 | 2016-12-09 | 2016-12-09 | N/A | 0 | 0 | 0 | 2 FS | 0
4 | Footing Cure For Bolts | TRUE |  | 1 | 2016-12-12 | 2016-12-12 | Bob Ross | 0 | 0 | 0 | 3 FS | 0
5 | Frame floor | TRUE |  | 2 | 2016-12-13 | 2016-12-14 | N/A | 0 | 0 | 0 | 4 FS | 0
6 | Sub floor plumbing | TRUE |  | 2 | 2016-12-15 | 2016-12-16 | N/A | 0 | 0 | 0 | 5 FS | 0
7 | Plumbing inspection | TRUE |  | 1 | 2016-12-19 | 2016-12-19 | N/A | 0 | 0 | 0 | 6 FS | 0
8 | Sub floor insulation | TRUE |  | 1 | 2016-12-20 | 2016-12-20 | General Contracting | 0 | 4 | 0 | 7 FS | 0
9 | Sheet floor | TRUE |  | 1 | 2016-12-21 | 2016-12-21 | N/A | 0 | 0 | 0 | 8 FS | 0
10 | Sub floor insulation inspection | TRUE |  | 1 | 2016-12-21 | 2016-12-21 | N/A | 0 | 0 | 0 | 8 FS | 0
11 | Cabinet measure | TRUE |  | 1 | 2016-12-22 | 2016-12-22 | N/A | 0 | 0 | 0 | 9 FS | 0
12 | Frame-walls | TRUE |  | 4 | 2016-12-22 | 2016-12-27 | N/A | 0 | 0 | 0 | 10 FS | 0
13 | Frame- roof | TRUE |  | 4 | 2016-12-28 | 2017-01-02 | N/A | 0 | 0 | 0 | 12 FS | 0
14 | Shear inspection | TRUE |  | 1 | 2017-01-03 | 2017-01-03 | General Contracting | 0 | 0 | 0 | 13 FS | 0
15 | Window install | TRUE |  | 1 | 2017-01-04 | 2017-01-04 | N/A | 0 | 0 | 0 | 14 FS | 0
16 | Gutter install | TRUE |  | 1 | 2017-01-05 | 2017-01-05 | Bob Ross | 0 | 0 | 0 | 15 FS | 0
17 | Hvac install- interior | TRUE |  | 2 | 2017-01-05 | 2017-01-06 | N/A | 0 | 0 | 0 | 15 FS | 0
18 | Prime (paint) wood windows | TRUE |  | 1 | 2017-01-05 | 2017-01-05 | N/A | 0 | 0 | 0 | 15 FS | 0
19 | Hot mop shower | TRUE |  | 1 | 2017-01-06 | 2017-01-06 | N/A | 0 | 0 | 0 | 18 FS | 0
20 | Rough Plumbing- top out | TRUE |  | 2 | 2017-01-09 | 2017-01-10 | N/A | 0 | 0 | 0 | 19 FS | 0
21 | Roof install | TRUE |  | 3 | 2017-01-11 | 2017-01-13 | General Contracting | 1 | 0 | 0 | 20 FS | 0
22 | Lath install | TRUE |  | 3 | 2017-01-16 | 2017-01-18 | N/A | 0 | 0 | 0 | 21 FS | 0
23 | Rough electrical | TRUE |  | 2 | 2017-01-19 | 2017-01-20 | N/A | 0 | 0 | 0 | 22 FS | 0
24 | Alarm Pre-Wire Install | TRUE |  | 1 | 2017-01-23 | 2017-01-23 | N/A | 0 | 0 | 0 | 23 FS | 0
25 | Frame inspection | TRUE |  | 1 | 2017-01-24 | 2017-01-24 | N/A | 0 | 0 | 0 | 24 FS | 0
26 | Plumber to have plumbing on test | TRUE |  | 1 | 2017-01-24 | 2017-01-24 | N/A | 0 | 0 | 0 | 24 FS | 0
27 | Insulation install | TRUE |  | 1 | 2017-01-25 | 2017-01-25 | N/A | 0 | 0 | 0 | 25 FS | 0
28 | Insulation inspection | TRUE |  | 1 | 2017-01-26 | 2017-01-26 | N/A | 0 | 0 | 0 | 27 FS | 0
29 | Drywall install | TRUE |  | 3 | 2017-01-27 | 2017-01-31 | N/A | 0 | 0 | 0 | 28 FS | 0
30 | Drywall inspection | TRUE |  | 1 | 2017-02-01 | 2017-02-01 | N/A | 0 | 0 | 0 | 29 FS | 0
31 | Stucco install- scratch coat | TRUE |  | 3 | 2017-02-02 | 2017-02-06 | N/A | 0 | 0 | 0 | 30 FS | 0
32 | Tape, Top, Texture | FALSE |  | 4 | 2017-02-02 | 2017-02-07 | N/A | 0 | 0 | 0 | 30 FS | 0
33 | Stucco scratch coat inspection | TRUE |  | 1 | 2017-02-07 | 2017-02-07 | N/A | 0 | 0 | 0 | 31 FS | 0
34 | Doors, casing, shelving install | TRUE |  | 2 | 2017-02-08 | 2017-02-09 | N/A | 0 | 0 | 0 | 32 FS | 0
35 | Stucco install- brown coat | TRUE |  | 3 | 2017-02-08 | 2017-02-10 | N/A | 0 | 0 | 0 | 33 FS | 0
36 | Interior paint | TRUE |  | 3 | 2017-02-10 | 2017-02-14 | N/A | 0 | 0 | 0 | 34 FS | 0
37 | Counter top/ tubdeck template | TRUE |  | 1 | 2017-02-13 | 2017-02-13 | N/A | 0 | 0 | 0 | 35 FS | 0
38 | Stucco install- finish coat | TRUE |  | 3 | 2017-02-13 | 2017-02-15 | N/A | 0 | 0 | 0 | 35 FS | 0
39 | Counter top/ tubdeck install | TRUE |  | 1 | 2017-02-14 | 2017-02-14 | N/A | 0 | 0 | 0 | 37 FS | 0
40 | Cabinet delivery/ install | TRUE |  | 2 | 2017-02-15 | 2017-02-16 | N/A | 0 | 0 | 0 | 36 FS | 0
41 | Tile backsplash | TRUE |  | 2 | 2017-02-15 | 2017-02-16 | N/A | 0 | 0 | 0 | 39 FS | 0
42 | Exterior paint | TRUE |  | 3 | 2017-02-16 | 2017-02-20 | N/A | 0 | 0 | 0 | 38 FS | 0
43 | Finish plumbing | TRUE |  | 1 | 2017-02-17 | 2017-02-17 | N/A | 0 | 0 | 0 | 41 FS | 0
44 | Measure shower glass | FALSE |  | 1 | 2017-02-17 | 2017-02-17 | N/A | 0 | 0 | 0 | 40 FS | 0
45 | Tile shower | TRUE |  | 3 | 2017-02-17 | 2017-02-21 | N/A | 0 | 0 | 0 | 40 FS | 0
46 | Finish electrical | TRUE |  | 2 | 2017-02-20 | 2017-02-21 | N/A | 0 | 0 | 0 | 43 FS | 0
47 | Shower glass install | TRUE |  | 1 | 2017-02-20 | 2017-02-20 | N/A | 0 | 0 | 0 | 44 FS | 0
48 | Downspout install | TRUE |  | 1 | 2017-02-21 | 2017-02-21 | N/A | 0 | 0 | 0 | 42 FS | 0
49 | Hvac install- exterior unit | TRUE |  | 1 | 2017-02-21 | 2017-02-21 | N/A | 0 | 0 | 0 | 42 FS | 0
50 | Flooring install | TRUE |  | 3 | 2017-02-22 | 2017-02-24 | N/A | 0 | 0 | 0 | 46 FS | 0
51 | Tile floor | TRUE |  | 3 | 2017-02-22 | 2017-02-24 | N/A | 0 | 0 | 0 | 45 FS | 0
52 | Baseover | TRUE |  | 1 | 2017-02-27 | 2017-02-27 | N/A | 0 | 0 | 0 | 50 FS | 0
53 | Install bath accessories, door hardware | TRUE |  | 1 | 2017-02-27 | 2017-02-27 | N/A | 0 | 0 | 0 | 50 FS | 0
54 | Texture touch up | TRUE |  | 1 | 2017-02-27 | 2017-02-27 | N/A | 0 | 0 | 0 | 50 FS | 0
55 | Cabinet touch up | FALSE |  | 1 | 2017-02-28 | 2017-02-28 | N/A | 0 | 0 | 0 | 52 FS | 0
56 | Paint baseboards, downspouts, touch up | TRUE |  | 1 | 2017-02-28 | 2017-02-28 | N/A | 0 | 0 | 0 | 52 FS | 0
57 | Final inspection | TRUE |  | 1 | 2017-03-01 | 2017-03-01 | N/A | 0 | 0 | 0 | 55 FS | 0
58 | Completion items | TRUE |  | 5 | 2017-03-02 | 2017-03-08 | N/A | 0 | 0 | 0 | 57 FS | 0
59 | Final Clean | TRUE |  | 1 | 2017-03-09 | 2017-03-09 | N/A | 0 | 0 | 0 | 58 FS | 0