## Schedules
Schedule - List - Sample Job (exported on Feb 18, 2022)
ID # | Title | Marked Complete | Phase | Dur. | Start | End | Assigned To | Confirm Accepted Count | Confirm Pending Count | Confirm Declined Count | Pred | Pred 1 Lag
1 | Architectural | TRUE |  | 15 | 2021-08-09 | 2021-08-27 | N/A | 0 | 0 | 0
2 | Engineering Design | TRUE |  | 10 | 2021-08-30 | 2021-09-10 | N/A | 0 | 0 | 0 | 1 FS | 0
3 | Permits | FALSE |  | 10 | 2021-09-13 | 2021-09-24 | N/A | 0 | 0 | 0 | 2 FS | 0
4 | Foundation | FALSE |  | 7 | 2021-09-27 | 2021-10-05 | N/A | 0 | 0 | 0 | 3 FS | 0
5 | Frame-Deck-Cornice | FALSE |  | 7 | 2021-10-06 | 2021-10-14 | N/A | 0 | 0 | 0 | 4 FS | 0
6 | HVAC Rough | FALSE |  | 5 | 2021-10-15 | 2021-10-21 | N/A | 0 | 0 | 0 | 5 FS | 0
7 | Plumbing Top Out | FALSE |  | 5 | 2021-10-15 | 2021-10-21 | Amazing Plumbing | 0 | 0 | 0 | 5 FS | 0
8 | Electrical Rough-In | FALSE |  | 5 | 2021-10-22 | 2021-10-28 | N/A | 0 | 0 | 0 | 6 FS | 0
9 | Install Roof | FALSE |  | 15 | 2021-10-22 | 2021-11-11 | N/A | 0 | 0 | 0 | 7 FS | 0
10 | A | FALSE |  | 1 | 2021-10-26 | 2021-10-26 | ABC Construction | 0 | 0 | 0
11 | A1 | FALSE |  | 1 | 2021-10-26 | 2021-10-26 | ABC Construction | 0 | 0 | 0
12 | A2 | FALSE |  | 1 | 2021-10-26 | 2021-10-26 | ABC Construction | 0 | 0 | 0
13 | A3 | FALSE |  | 1 | 2021-10-26 | 2021-10-26 | ABC Construction | 0 | 0 | 0
14 | Structured Wiring Rough | FALSE |  | 5 | 2021-10-29 | 2021-11-04 | Joe's Remodeling | 0 | 0 | 0 | 8 FS | 0
15 | Insulation Install | FALSE |  | 2 | 2021-11-05 | 2021-11-08 | Joe's Remodeling | 0 | 0 | 0 | 14 FS | 0
16 | Drywall | FALSE |  | 5 | 2021-11-09 | 2021-11-15 | N/A | 0 | 0 | 0 | 15 FS | 0
17 | Exterior Masonry | FALSE |  | 30 | 2021-11-09 | 2021-12-20 | N/A | 0 | 0 | 0 | 15 FS | 0
18 | Interior Millwork | FALSE |  | 15 | 2021-11-16 | 2021-12-06 | N/A | 0 | 0 | 0 | 16 FS | 0
19 | Countertop Install | FALSE |  | 5 | 2021-12-07 | 2021-12-13 | Amazing Plumbing | 0 | 0 | 0 | 18 FS | 0
20 | Install Tile & Stone | FALSE |  | 20 | 2021-12-07 | 2022-01-03 | N/A | 0 | 0 | 0 | 18 FS | 0
21 | Paint | FALSE |  | 10 | 2021-12-07 | 2021-12-20 | N/A | 0 | 0 | 0 | 18 FS | 0
22 | Hardwood Flooring Install | FALSE |  | 5 | 2021-12-14 | 2021-12-20 | N/A | 0 | 0 | 0 | 19 FS | 0
23 | Plumbing Fixtures Install | FALSE |  | 5 | 2021-12-14 | 2021-12-20 | Amazing Plumbing | 0 | 0 | 0 | 19 FS | 0
24 | Pool Shell | FALSE |  | 5 | 2021-12-14 | 2021-12-20 | N/A | 0 | 0 | 0 | 19 FS | 0
25 | Flatwork | FALSE |  | 5 | 2021-12-21 | 2021-12-27 | Amazing Plumbing | 0 | 0 | 0 | 24 FS | 0
26 | HVAC Finish | FALSE |  | 1 | 2021-12-21 | 2021-12-21 | N/A | 0 | 0 | 0 | 23 FS | 0
27 | Interior Hardware Install | FALSE |  | 3 | 2021-12-21 | 2021-12-23 | N/A | 0 | 0 | 0 | 23 FS | 0
28 | Light Fixture Install | FALSE |  | 2 | 2021-12-21 | 2021-12-22 | N/A | 0 | 0 | 0 | 23 FS | 0
29 | Hardwood Floors Finish | FALSE |  | 4 | 2021-12-23 | 2021-12-28 | N/A | 0 | 0 | 0 | 28 FS | 0
30 | Mirrors and Glasswork | FALSE |  | 1 | 2021-12-23 | 2021-12-23 | N/A | 0 | 0 | 0 | 28 FS | 0
31 | Structured Wiring Trim | FALSE |  | 4 | 2021-12-24 | 2021-12-29 | N/A | 0 | 0 | 0 | 27 FS | 0
32 | Fences and Gates | FALSE |  | 2 | 2021-12-28 | 2021-12-29 | N/A | 0 | 0 | 0 | 25 FS | 0
33 | Landscaping/Finish Grade | FALSE |  | 5 | 2021-12-28 | 2022-01-03 | N/A | 0 | 0 | 0 | 25 FS | 0
34 | Appliance Installation | FALSE |  | 1 | 2021-12-29 | 2021-12-29 | Amazing Plumbing | 0 | 0 | 0 | 29 FS | 0
35 | Rough Punchout | FALSE |  | 4 | 2021-12-30 | 2022-01-04 | N/A | 0 | 0 | 0 | 34 FS | 0
36 | Final touch up, punchout, clean. | FALSE |  | 5 | 2022-01-05 | 2022-01-11 | N/A | 0 | 0 | 0 | 35 FS | 0
37 | Completion | FALSE |  | 1 | 2022-01-12 | 2022-01-12 | N/A | 0 | 0 | 0 | 36 FS | 0
38 | TEST | FALSE |  | 1 | 2023-06-02 | 2023-06-02 | N/A | 0 | 0 | 0